## Introduction
Project Name |  |  | PO3_DGW
Ref Document |  | SRS
Ref Version |  | 1
Auther |  | Tarek Sharaby
Last update |  | 30/01/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 30/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
30/01/2020 | TSH | V1.1 | SRS | 1 | You should manage the status table of the document as follows : Document : xxxxxx Auther : xxxxxx Date : xxxxxx "fo last update " Version : xxxx Status : Darfte , Proposed , Reviewed , Released | Accepted | Open | Added status table as required
30/01/2020 | TSH | V1.1 | SRS | Document History | At the creation of the document it should be draft , then after first cross review and fixing the open points you can changed it to Proposed as I can see the status become proposed without any review , why ? | Accepted | Open | There was a misconcept but it is modified | Accepted
30/01/2020 | TSH | V1.1 | SRS | ALL | There is no refernce table for the refernce document it should be like this : Ref Docu : xxxxx Version : xxxx Status : xxx Ex the reference for SRS means the input document that enables you to meke the SRS , so the inputs are : - CYRS , and HIS_ if it contains SW req , if not then CYRS is the input for SRS | Accepted | Open | Added reference document | Refused
30/01/2020 | TSH | V1.1 | SRS | ALL | There is no Software context which decrib the blocks of SW how they are going to communicate in terms of sw features | Accepted | Open | Added SW Context diagram descirbing the whole sw signals
30/01/2020 | TSH | V1.1 | SRS | Software requirement | The goal of the SW req is to descrip what in specific software shall do , so you shall keep the SRS req atmoic means do one thing , and try to make an input and out put for it as much as you can | Accepted | Open | modified all the requirements to atomic requirements | Open
30/01/2020 | TSH | V1.1 | SRS | Software requirement | you could represent each req in a table for more organization this table as follows : Req ID : xxx Description : xxxxxx Coverage : the CYRS req Input : xxx if you have it output : if you have | Accepted | Open | modified the requirements to the required table template | Resolved
30/01/2020 | TSH | V1.1 | SRS | Software requirement | PO3_DGW_SRS_01_V01: this req doesn't descrip the SW but it descrip the system wise "upper Level" , as the goal of SRS is to descrip I details what sw shall do. The SRS : should be something atomic SW can do with clear input and output : for how the user can change the current time , is by pressing a button that SW shall read then check its value and update the correct variables or signals inside the SW , and So on .... | Accepted | Open | modified this requirement to sw not system requirement
30/01/2020 | TSH | V1.1 | SRS | Software requirement | PO3_DGW_SRS_02_V01 : also this one is in a high level description and it is not saying anything of HOW SW SHALL DO THAT? For instance : you can say SW shall display the time formate : hh: mm : Sec Am/PM | Accepted |  | modified this requirement to sw not system requirement
30/01/2020 | TSH | V1.1 | SRS | Software requirement | All req of SRS need to be reconsidered as above methodolgy of writing the SRS | Accepted |  | modified | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open