## Introduction
Project Name |  |  | Digital Watch
Ref Document |  | CYRS
Ref Version |  | V1.5
Auther |  | Tarek Sharaby
Last update |  | 2020-09-02
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 24/01/2020 | Initial creation
0.2 | T.Sharaby |  | 2020-09-02 | Update the status for each req

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
24/01/2020 | T.Sharaby | V1.2 | CYRS | Page 1 | Document statuc table : you should put the status of the document which exist in the start in a table , this table holds the following info "Document name , Suther , Version , Auther , Last update Date" | Accepted | Resolved | This is already included in the document history
24/01/2020 | T.Sharaby | V1.2 | CYRS | Document History | First creation should not be proposed , it should be draft and after the cross review is done and points fixed then it could be proposed , because as I can see both version are proposed , and the change it only the formate so it should stay Draft - Document history has to be at the start | Accepted | Resolved | Modified, and document history is moved to the start of the document | Accepted
24/01/2020 | T.Sharaby | V1.2 | CYRS | ALL | There is no Reference table for the reference document , even CYRS should have one and the refernce is the customer req for the product | Accepted | Resolved | The reference table that references each requirement to its parent requirement in the CRS document is at the end of the CYRS document | Refused
24/01/2020 | T.Sharaby | V1.2 | CYRS | ALL | The CYRS req shall not say the software shall do xxxx , as the CYRS descrip the overall system , then SRS will descrip the SW So CYRS shall be more abstracted. Ex: 4.1 Req_ PO3_DGW_CYRS_01_V01 you can say : the system use time formate of 00:00:00 PM/AM because the req you mention is more likely sw not system level | Accepted | Resolved | Modified as a system and not software requirements
24/01/2020 | T.Sharaby | V1.2 | CYRS | ALL | 4.2 Req_ PO3_DGW_CYRS_02_V01 : Here you want to defient he HW req then the goal from HW is to describ the HW , but in the req nothing related to HW as it more likely SW So if you want to describ the HW then for Ex : you can say The system shall use 16*2 display to show different mode ,, and so on | Refused | Resolved | As the HSI is the document related to the chosen HW components so in the CYRS for example a displayer in the high level and in the HSI its specified to a 16*2 lcd | Open
24/01/2020 | T.Sharaby | V1.2 | CYRS | ALL | 4.3 Req_ PO3_DGW_CYRS_03_V01 : You can list all Req in hardware software interface document , because the notification is based on SW but the sound is coming from Buzzer fo you can describ the conection for the HW and so on | Refused | Resolved | Thiss requirement describes a high level relation between the HW component""Buzzer" that will be referenced to the HIS and a SW requirement"That buzzer is on when specific time is hit" that will be referenced to the SRS | Resolved
24/01/2020 | T.Sharaby | V1.2 | CYRS | ALL | All Req need to be updated with system level prospective not SW prospective | Accepted | Resolved | Modified
2020-09-02 | T.Sharaby | V1.5 | CYRS | ALL | There is lots of use cases are not mentioned in terms of system req Like : - How to navigate between modes - what are the functions of each button in each mode - how to adjust the time and minute for each mode - etc |  | Open
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open