## Simple Gantt Chart - BLANK
PP
PROJECT TITLE | Digital Watch
DATE | 21-1-2020
[9 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | Task | TASK | START | EXPECTED | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | Description | OWNER | DATE | END DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | CYRS Documentation | first creation | Mostafa-Hammam | 21-1-2020 | 22-1-2020 | 22-1-2020 | 1 | 100%
2 | SRS Documentation | first creation | Marina-Qandeel | 22-1-2020 | 22-1-2020 | 23-1-2020 | 1 | 100%
3 | HSI Documentation | first creation | Basma | 22-1-2020 | 22-1-2020 | 23-1-2020 | 1 | 100%
4 | CYRS Documentation | update CYRS according to its cross review | Mostafa Nader | 2020-03-02 | 2020-04-02 | 2020-04-02 | 1 | 100%
5 | HSI Documentation | update HSI according to its cross review | Basma | 2020-03-02 | 2020-04-02 | 2020-04-02 | 1 | 100%
6 | CYRS Cross Review | Cross Review over CYRS document | Hammam | 2020-04-02 | 2020-05-02 | 2020-05-02 | 1 | 100%
7 | HSI Cross Review | Cross Review over HSI document | Ahmed Qandeel | 2020-04-02 | 2020-05-02 | 2020-05-02 | 1 | 100%
8 | SRS Documentation | update SRS according to its cross review | Marina | 2020-05-02 | 2020-07-02 | 2020-07-02 | 2 | 100%
9 | SRS Cross Review | Cross Review over SRS document | Mostafa Nader | 2020-07-02 | 2020-08-02 | 2020-08-02 | 1 | 100%
10 | SRS Documentation | update last version of SRS according to its cross review | Mostafa Nader | 19/2/2020 | 20/2/2020 | 20/2/2020 | 1 | 100%
11 | SRS Cross Review | Cross Review over SRS document | Marina | 20/2/2020 | 21/2/2020 | 20/2/2020 | 1 | 100%
12 | SRS Documentation | update Requirment tables and SW Context diagram | Mostafa Nader | 22/2/2020 | 23/2/2020 |  | 1 | 0%
at SRS document according to its Cross Review