## Simple Gantt Chart - EX
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Leon W | 2023-03-12 | 2023-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2023-03-15 | 2023-03-16 | 1 | 100%
1.2 | Research | Pete S | 2023-03-15 | 2023-03-21 | 6 | 90%
1.3 | Projections | Steve L | 2023-03-16 | 2023-03-22 | 6 | 40%
1.4 | Stakeholders | Allen W | 2023-03-17 | 2023-03-22 | 5 | 70%
1.5 | Guidelines | Malik M | 2023-03-18 | 2023-03-22 | 4 | 60%
1.6 | Project Initiation | Malik M | 2023-03-23 | 2023-03-23 |  | 50%
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Steve L | 2023-03-24 | 2023-03-28 | 4 | 5%
2.2 | Budget | Allen W | 2023-03-29 | 2023-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  |  | 0%
2.4 | Risk Management | Malik M |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status and Tracking | Pete S |  |  |  | 0%
3.2 | KPIs | Leon W |  |  |  | 0%
3.2.1 | Monitoring | Kylie R |  |  |  | 0%
3.2.2 | Forecasts | Kylie R |  |  |  | 0%
3.3 | Project Updates | Pete S |  |  |  | 0%
3.3.1 | Chart Updates | Malik M |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  |  | 0%
4.2 | Quality Deliverables | Allen W |  |  |  | 0%
4.3 | Effort and Cost Tracking | Malik M |  |  |  | 0%
4.4 | Project Performance | Malik M |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## Simple Gantt Chart - BLANK
PP
PROJECT TITLE | Digital Watch
DATE | 21-1-2020
[8 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | EXPECTED | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | END DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | CYRS Documentation | Mostafa-Hammam | 21-1-2020 | 22-1-2020 | 22-1-2020 | 1 | 100%
2 | SRS Documentation | Marina-Qandeel | 22-1-2020 | 22-1-2020 | 23-1-2020 | 1 | 100%
3 | HSI Documentation | Basma | 22-1-2020 | 22-1-2020 | 23-1-2020 | 1 | 100%
4 | CYRS Documentation | Mostafa Nader | 2020-03-02 | 2020-04-02 |  | 1 | 0%
5 | HSI Documentation | Basma | 2020-03-02 | 2020-04-02 |  | 1 | 0%
6 | CYRS Cross Review | Hammam | 2020-04-02 | 2020-05-02 |  | 1 | 0%
7 | HSI Cross Review | Ahmed Qandeel | 2020-04-02 | 2020-05-02 |  | 1 | 0%
8 | SRS Documentation | Marina | 2020-05-02 | 2020-07-02 |  | 2 | 0%
9 | SRS Cross Review | Mostafa Nader | 2020-07-02 | 2020-08-02 |  | 1 | 0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.